## Parking Co-Chair
Parking Co-Chair Responsibilities |  | Parking, Permits & Barricades
Planning: Chevy's in the Park
| Assignment | Assigned to: (Contact Name) | Phone Number | Initiated | Scheduled | Completed | Comments
1 | Assist Chairman/attend meetings for obtaining permits from DCCP & City of Chandler (COC) | Brad Ryan Dom Lovino |  | 2018-06-18 | 2018-06-20 |  | How many days out? Contact Names for DCCP & City of Chandler. First meeting on 6/20. Where do you find the paperwork?
2 | Create a complete parking plan with appropriate space for all car classes, vendors, PFH, etc. | Dom Lovino |  | 2018-06-14 |  |  | Is there a copy from 2017 Show? There was a list of classes. I have a draft created, waiting on review and copy of from last show.
3 | Order barricades & coordinate the placement date/time with barricade company | Dom Lovino |  |  |  |  | Brad to provide Contact Name & phone #. Need to barricade 3 entrances. How many days out? Install by 4pm?? on 10/26,
4 | Coordinate the pickup date/times with barricade company | [5 empty] | Remove after 3pm on 10/27
5 | Provide training for parking cars, see if John Marsh and Mike Mileskiewicz can help demonstrate |  |  | 2018-06-14 |  |  | Created draft of training document. Need review and approval from Chair
6 | Sign up sheet for volunteers for parking and DOS setup |  |  | 2018-06-14 |  |  | Created draft document. Need review and approval from Chair
7 | Need 5 radios for Car show to communicate to PA's |  |  | 2018-06-14 |  |  | Does club have them? I have some if I can find them.
8 | Contact Earnhardt for Car/Truck to display at Show | [5 empty] | Contact Name & Phone #. Deliver by 9:00 on 10/27
Day of Show (before)
| Assignment | Assigned to: (Contact Name) | Phone Number | Initiated | Scheduled | Completed | Comments
1 | Install ‘No Overnight Parking’ signs on closed streets the afternoon before show |  |  | 2018-06-14 | 2018-10-26 |  | Volunteers? Is a there a sheet already created by COC (City of Chandler)? Or is it part of the Barricade?
2 | Pick up A-frames from City Locker and place at appropriate street entrances |  |  |  | 2018-10-27 |  | Can we check sizes to see what type of signage can be put on them?
3 | Pick-up and set out cardboard trash containers provided by city (in storage locker) |  |  |  | 2018-10-27 |  | 8 - 10 should be enough. Need 45 gallon garbage bags.
4 | Assign Volunteers to parking positions and hand out vests and flags/ Radios |  |  | 2018-06-14 |  |  | Need 13 vests, 5 radios
5 | Provide copies of the parking plan map for workers to park cars accordingly |  |  |  | 2018-10-27
6 | Have “Drip Pans”, washers, detergent, water and brush available for vehicles that may leak oil | [5 empty] | Is this for the Ramada only? Who has from previous shows?
7 | Collect Vests and flags and place in box by CCA Booth |  |  |  | 2018-10-27 |  | Should be able to turn in after 10am/or all cars parked.
Day of Show (After)
| Assignment | Assigned to: (Contact Name) | Phone Number | Initiated | Scheduled | Completed | Comments
1 | Pick up A-frames from appropriate street entrances and place back in City Locker |  |  |  | 2018-10-27
2 | Pick-up and put away cardboard trash containers provided by city (in storage locker) |  |  |  | 2018-10-27 |  | Where do full garbage bags go?
3 | Retrieve “Drip Pans” Use detergent, water and brush to clean up oil from vehicles that have leaked |  |  |  | 2018-10-27 |  | Need a sign up (2) for after show.

## Public Relations Co-Chair
Public Relations Co-Chair Responsibilities |  |  | Publicity and Vendors
Planning: Chevy's in the Park
| Assignment | Assigned to: (Contact Name) | Phone Number | Initiated | Scheduled | Completed | Comments
1
2
3
4
5
6
Day of Show (before)
| Assignment | Assigned to: (Contact Name) | Phone Number | Initiated | Scheduled | Completed | Comments
1
2
3
4
5
6
7
Day of Show (After)
| Assignment | Assigned to: (Contact Name) | Phone Number | Initiated | Scheduled | Completed | Comments
1
2
3

## Registration Co-Chair
Registration Co-Chair Responsibilities |  |  | Registration
Planning: Chevy's in the Park
| Assignment | Assigned to: (Contact Name) | Phone Number | Initiated | Scheduled | Completed | Comments
1
2
3
4
5
6
Day of Show (before)
| Assignment | Assigned to: (Contact Name) | Phone Number | Initiated | Scheduled | Completed | Comments
1
2
3
4
5
6
7
Day of Show (After)
| Assignment | Assigned to: (Contact Name) | Phone Number | Initiated | Scheduled | Completed | Comments
1
2
3

## Awards Co-Chair
Awards Co-Chair Responsibilities |  |  | Awards, Signage & Raffle
Planning: Chevy's in the Park
| Assignment | Assigned to: (Contact Name) | Phone Number | Initiated | Scheduled | Completed | Comments
1
2
3
4
5
6
Day of Show (before)
| Assignment | Assigned to: (Contact Name) | Phone Number | Initiated | Scheduled | Completed | Comments
1
2
3
4
5
6
7
Day of Show (After)
| Assignment | Assigned to: (Contact Name) | Phone Number | Initiated | Scheduled | Completed | Comments
1
2
3